IME Offline Software upgrade from version 7.1 to version 10

STATEMENT OF WORK (SOW) 59

This Statement of Work #59 (the “SOW”) effective as of July 1st,  2025 (the “Effective Date”), is made by and between Freedom Mobile Inc. (“Customer” or “Freedom”) and Intec Billing Canada Ltd. (“Intec” or “CSG”) pursuant to, and shall be governed by the terms and conditions of the Master Software License and Services Agreement entered into between Customer and Intec as of April 10, 2009, as amended (the “Agreement”) and describes certain specific Services to be performed by CSG for Customer.  All capitalized terms used herein and defined in the Agreement shall have the same meanings as set forth in the Agreement.

- Background

Freedom currently has a license for the use of CSG’s Intermediate (IME) Software. Freedom has initiated a project whereby CSG will upgrade it from its current version of 7.1 to version 10.0  referred to as “Project”, which is contracted under this SOW.

- Objective

The objective of this SOW is to outline the activities in order for CSG to perform the services related to the upgrade of the Intermediate (“IME”) Software.

- Scope of Work (the “Services”)

CSG will provide resources that will be engaged for the period described in Section 8.0 further below. CSG will collaborate with Customer in support of the Project by performing the activities set forth below by migrating and upgrading Intermediate (IME) in the environments detailed in this Section 3.0. (collectively, the “Services”):

- Production Environment (“Production Environment”)

- The Production Environment phase consists of one (1) production IME node.

- CSG will create a Pre-Installation Checklist (“PIC”) for Freedom to use and prepare the new server for installation of IME version 10.0 (if Freedom is hosting the server).

- CSG will install IME v10.0 on the new application server node.

- CSG will copy existing scripts, system and business configurations and parameters from IME version 7.1 to the IME version 10.0.

- CSG will configure changes to CSG DASH reporting (if applicable) to pull IME information from the new production servers.

- Non-Production Environment (“Test Environment”)

- Test Environment consists of one (1) user acceptance testing (“UAT”) IME node, one (1) solution integration testing (“SIT”) IME node, and one (1) development (“DEV”) IME node.

- CSG will create a Pre-Installation Checklist (PIC) for Freedom to use to prepare the new servers for installation of IME version 10.0 (if Freedom is hosting).

- CSG will install IME version 10.0 on new application server nodes.

- CSG will copy existing scripts, system and business configurations and parameters from IME version 7.1 to the IME version 10.0.

- Testing Approach (CSG will support Freedom’s IME team to plan and execute testing services as follows)

- Test Cycles:

    - Freedom will be responsible for UAT, regression testing, end-to end integration testing. HA testing and performance testing.

    - CSG will provide support in the form of questions and defect fixes resulting from the above-mentioned testing cycles. No new functionality will be included as part of this support and if required will be addressed through the Change Request process.

- UAT testing exit criteria:

- 100% execution of all test cases with exception in cases where the environment or test setup does not allow execution of test case

- No High or Critical defects in open status

- CSG’s IME product documentation will be made available to Freedom.

- Deployment.

- Creation of Methods of Procedure (“MOP”) for the final cutover to production.

- Exclusions

The following activities are not included in the scope of this SOW:

- Changes to the business logic and business rules, other than for inbound roaming usage

- Any customization to reports

- Any changes to the current alarm and alert functionality

- Any item not explicitly included in this scope shall be deemed excluded

- Deliverables (the “Deliverables”)

Pursuant to this SOW, CSG will provide the following Deliverables to Freedom as part of the Services: none which are subject to approval or acceptance:

- Pre upgrade Check List

- Product documentation

- Customer Responsibilities

Delays in performing tasks assigned to Customer or Customer’s responsibilities set forth in this SOW may result in additional CSG effort and cost to Customer to start and/ or complete the Services described in this SOW, and/or may delay the completion of the Services. Any additional costs identified as a result of any such delays will be managed through the Change Request process specified in Section 6.3 of the Agreement.

Customer’s responsibilities under this SOW include:

- Providing CSG with access to the Customer servers, tools and environments as necessary to perform the Services

- Coordinating, facilitating communication, and obtaining the required information and support in order for CSG to be able to perform the Services

- Managing and executing all UAT testing activities and providing approvals on the delivered functionality within ten (10) business days from deployment to UAT environment

- Freedom will provide required resources to work with CSG consultants

- Providing the Pre-Installation Checklist results of the verification scripts once the required hardware and software for each environment in scope is in place, if Freedom is hosting the servers

- Establishing backups of the new environments, if hosted at Freedom

- Establishing and maintaining VPN connectivity from CSG networks to the new IME application servers

- Establishing and maintaining connectivity between the IME servers installed and the same upstream and downstream network interfaces that are in place for the current IME environment

- Configuring the upstream or downstream network elements to communicate with the new IME server.  For example, configuring allow lists, or exchanging keys

- Performing regression testing in DEV, SIT, and UAT of the upgraded IME version

- Updates to IME scripts discovered through testing to be incompatible with the new IME version

- Decommissioning the legacy IME application servers after Go-live

- Providing a UNIX administrator, firewall and network engineer to support CSG

- Create the MOP for the cutover to production in case this application is hosted outside of CSG’s AWS

- CSG Responsibilities

CSG’s responsibilities under this SOW includes:

- Providing the Pre-Installation Checklist including scripts for hardware verification

- Synchronizing the current test and production patch levels

- Reconfiguring in scope applications for the new hostnames

- Validating the migration on each environment in scope

- Create the MOP for the cutover to production in case this application is hosted inside CSG’s AWS

- Assumptions

The Services pricing and projected completion date are based upon the following assumptions to the extent such assumptions are necessary to the performance of the Services. Any additional costs identified as a result of any deviations from these assumptions will be managed through the Change Request process specified in Section 6.3 of the Agreement.

- The upgrade will require downtime in which activation in the Production Environments will not be available. This activity will be carried out in a planned maintenance window

- All Services will be conducted remotely using VPN access to Freedom servers on-premises

- Delivery Schedule

In the event Customer fails to perform its responsibilities as set forth in Section 6 above, then such completion date will be extended accordingly in accordance with the Change Request process described in the Agreement.

The table below provides an indicative Project schedule to be initiated in the kick off day which shall be determined by the Parties (Kick Off Date):

The User Acceptance Test Period is assumed and limited to the allowance shown below. Any extension to this duration will be managed under the Change Request process.

| Description | Allowance |
| --- | --- |
| CSG will provide UAT support for the following continuous durations of UAT | - weeks |

- Commercial Terms

  - Pricing

CSG will provide the Services described in this SOW for a fixed fee of One Hundred and Twenty Thousand, Five Hundred and Fifty-Three Canadian Dollars (CAD $120,553). This fixed fee is one (1) part of a group of six (6) fixed fees SOWs, namely SOWs 54, 55, 56, 57, 58 and 59. The combined fixed fee for these SOWs is Three Million, Three Hundred and Seven Thousand, Four Hundred and One Canadian Dollars (CAD$ 3,307,401), therefore they must be executed on the same day. In the event that one of these SOWs is not executed on the same day, CSG reserves the right issue a change request via Change Management process to adjust the fee in accordance with how many of those six (6) SOWs are executed.

This fixed fee does not include any travel and living expenses.

In the event that during performance of the Services hereunder, CSG requires any travel and/or related travel expenses, CSG will obtain prior written approval by Freedom, before incurring such expenses and furnish required documentation prior to submitting such expenses.

  - Invoicing

The fees for Services provided herein will be invoiced by CSG to Customer as follows:

| Milestone | Payment Milestone Date | Allocated Fees in CAD $ |
| --- | --- | --- |
| Environments setup completed | Month 1 | $30,138 |
| IME V10 configured | Month 2 | $30,138 |
| UAT Support Completed | Month 3 | $30,138 |
| Production Ready | Month 4 | $30,139 |
| Total fixed SOW price |  | $120,553 |

The payment of all invoices shall be governed by the terms and conditions in the Agreement.  For avoidance of doubt, excluded from the prices herein are taxes or duties applicable on the Services, which shall be the responsibility of Customer.

Should there be a delay on the delivery of any Milestone event defined above, regardless of the reason, CSG expects that the “Payment Milestone Date” is not going to be affected and it will proceed with the respective invoicing of the Allocated Fees in accordance with the respective Payment Milestone Date provided above.

  - Term

The term of this SOW will begin as of the Effective Date and expire upon completion of the Services, not to exceed a period of four (4) months as from the Kick Off Date (the “SOW Term”), unless mutually agreed upon via the Change Request process.

- Remote Network Access

CSG will be granted remote access to Customer exclusively for use in execution of the Services described in this SOW. CSG acknowledges and agrees that access is permitted solely for the purpose of CSG fulfilling its obligations to provide the Services or Deliverables described under this SOW. CSG acknowledges that its obligations under Section 12 of the Agreement apply to the Confidential Information of Customer that is disclosed to CSG as a result of such remote access. In order for Customer to be able to activate the remote access, Intec shall, not later than seven (7) days of the commencement of the Services hereunder, provide project manager (or designated lead) the full names and email addresses of all CSG personnel performing Services under this SOW who will require such remote access. CSG is responsible to notify Customer of any changes to the personnel, whether to remove or add individuals, at least seven (7) days in advance of such change.

IN WITNESS WHEREOF, the Parties hereto, intending to be legally bound, have caused this SOW to be duly executed as of the SOW Effective Date written above.

Freedom Mobile, Inc.	Intec Billing Canada LTD.

By: 						          		By:

{Signature} 						          	{Signature}

{Printed Name} 					          	{Printed Name}

{Title} 							           	{Title}

By:

{Signature}

{Printed Name}

{Title}